## Sheet1
Date | Activity | Task | Status | Hours | Scope Creep | Activity | x/y | P | %
2015-07-06 | Theory | Initiate project and familiarize with subject. | Done | 3 |  | Total Hours | 113.5
2015-07-07 | Integration | Download and test C++ Example. | Done | 6 |  | Total 8h Days | 14.1875 | 0.34604
2015-07-08 | Integration | Download, build and test latest version of the test harnes. | Done | 3 |  | Total Actual Days | 41 | 2.8899 |  | <- Fix the day counts, so that they reflect unique days.
2015-07-08 | Integration | Create new random agent. Name = "Randomizer" | Done | 3 |  | - | 3 / 41 | 0.073171 | 7.3171
2015-07-08 | Theory | Manualy test procedural theory. | Done | 7 |  | Theory | 8 / 41 | 0.19512 | 19.5122
2015-07-08 | Theory | Test state compresion ratio using run length compression. It is about 20%. | Done | 7 | 1 | Integration | 7 / 41 | 0.17073 | 17.0732
2015-07-08 | Integration | Investigate the command line parameter that run.bat should accept. | Done | 1 |  | Code - Replay Viewer | 31 / 41 | 0.7561 | 75.6098
2015-07-09 | Code - Replay Viewer | Reformat code to comply with Google coding standards. | Done | 2 |  | Integration - Test Agent | 0 / 41 | 0 | 0
2015-07-09 | Code - Replay Viewer | Convert the ConsoleApplication class, to an abstract class. | Done | 2 |  | Code - Agent Trainer | 0 / 41 | 0 | 0
2015-07-09 | Code - Replay Viewer | Derive a new application class from the abstract ConsoleApplication class. | Done | 2 |  | Code - Competition Agent | 0 / 41 | 0 | 0
2015-07-10 | Code - Replay Viewer | BUG: Compilation bug. | Done | 8
2015-07-11 | Code - Replay Viewer | BUG: Compilation bug. | Done | 8
2015-07-12 | Code - Replay Viewer | BUG: Compilation bug. | Done | 4
2015-07-13 | Code - Replay Viewer | BUG FIX: We were referencing constants before they were devlared. | Done | 4
2015-07-14 | Code - Replay Viewer | Upgrade usability of ConsoleApplication, and test abstract functionality. | Done | 3
2015-07-14 | Code - Replay Viewer | Test new derived class. | Done | 2 | 1
2015-07-15 | Code - Replay Viewer | Move all string and application info functions to the derived class. | Done | 3
2015-07-16 | -
2015-07-17 | -
2015-07-18 | Code - Replay Viewer | Created the framework for the TextBuffer class. | Done | 4
2015-07-19 | Theory | Revised C++11 functions and pointers. | Done | 5
2015-07-19 | Code - Replay Viewer | BUG: Indexing bug. | Done | 4
2015-07-20 | Code - Replay Viewer | BUG FIX: There was an error in the linear offset formula. The formula should be: i = r w + c - 1 | Done | 1
2015-07-20 | Code - Replay Viewer | Completed the constructor, initialize, and draw_char. | Done | 5
2015-07-21 | Theory | Find out to clear the console. | Done | 0.5
2015-07-21 | Theory | Find out about console cursor move. | Done | 0.5
2015-07-21 | Code - Replay Viewer | Implement clear_console function in ConsoleApplication | Done | 0.5
2015-07-21 | Code - Replay Viewer | Implement move_to function in ConsoleApplication | Done | 0.5
2015-07-21 | Code - Replay Viewer | Complete draw string. | Done | 2
2015-07-22 | Theory | Revised C++11 random number generators. | Done | 4 | 1
2015-07-23 | Integration | Added a sleep function to StaticUtility | Done | 0.5 | 1
2015-07-23 | Code - Replay Viewer | Connected up the command line replay path argument. | Done | 0.5
2015-07-23 | Integration | Added a to_lower function to StaticUtility. | Done | 0.5 | 1
2015-07-24 | -
2015-07-25 | Code - Replay Viewer | Implemented basic vertical and horizontal line drawing functions. | Done | 2
2015-07-26 | Code - Replay Viewer | Implemented smart ASCII overlay. | Done | 1.5
2015-07-26 | Code - Replay Viewer | Implemented draw rectangle. | Done | 1.5
2015-07-26 | Code - Replay Viewer | Implemented draw filled rectangle. | Done | 1.5
2015-07-26 | Code - Replay Viewer | Implemented shaded block draw. | Done | 1.5
2015-07-27 | Code - Replay Viewer | console_text_buffer Save. | Done | 1
2015-07-27 | Code - Replay Viewer | console_text_buffer buffer read functions. | Done | 1
2015-07-27 | Code - Replay Viewer | Implement smart overlay. | Done | 1
2015-07-27 | Code - Replay Viewer | Implement and test TextBuffer class. | Done | 1
2015-07-28 | Code - Replay Viewer | Read state files from enumerated folders. | Done | 5
| Theory | Why is using System bad? | Next
| Code - Replay Viewer | Open and read log file. | Next
| Code - Replay Viewer | Implement single frame display. | Next
| Code - Replay Viewer | Implement replay animation. | Next
| Integration | Work out how to build from the command line.
Test Randomizer1 in the test harnes.
Upload Randomizer to the Dashboard.
Test in Randomizer1 with the dashboard.
Create application framework for RL learner.
Study relationship between RL and ANN generelization value function.

## Sheet2
3
1
7
7
7
1
1
3
1
3
1
1
3
1
3
1
3
1
9
7
7
3
3
77